## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | Real-Time Social Media Analytics Pipeline
PROJECT MANAGER | Solo Learning Project
PROJECT DELIVERABLE | Bluesky Analytics System with Dashboard
SCOPE STATEMENT | 3-Phase Learning Project: Data Pipeline → ML Analytics → Integration
START DATE | 06/09/2025 | END DATE | 08/25/2025 | OVERALL PROGRESS | 0%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
PHASE 1: DATA PIPELINE FOUNDATION
Setup Development Environment | Self | 06/09/2025 | 06/13/2025 | 5 | Not Started | Python, Docker, Git repo
Bluesky API Integration | Self | 06/09/2025 | 06/13/2025 | 5 | Not Started | API access + basic data collection
Local Kafka Setup | Self | 06/16/2025 | 06/20/2025 | 5 | Not Started | Single broker, basic producer/consumer
Bluesky → Kafka Integration | Self | 06/16/2025 | 06/27/2025 | 8 | Not Started | Live data flowing to Kafka
Azure Account Configuration | Self | 06/23/2025 | 06/27/2025 | 5 | Not Started | Storage + SQL database setup
Basic Spark Processing | Self | 06/30/2025 | 07/04/2025 | 5 | Not Started | Read Kafka, process, store Azure
End-to-End Pipeline Test | Self | 07/07/2025 | 07/11/2025 | 5 | Not Started | 24hr unattended operation
Phase 1 Documentation | Self | 07/07/2025 | 07/11/2025 | 5 | Not Started | Setup guides + lessons learned
PHASE 2: ML ANALYTICS DEVELOPMENT
Sentiment Analysis Implementation | Self | 07/14/2025 | 07/25/2025 | 8 | Not Started | VADER + RoBERTa ensemble
Model Testing on Kaggle Data | Self | 07/21/2025 | 07/25/2025 | 5 | Not Started | Validate accuracy on known datasets
Trend Detection Algorithms | Self | 07/28/2025 | 08/01/2025 | 5 | Not Started | Hashtag frequency + anomaly detection
User Behavior Analytics | Self | 07/28/2025 | 08/01/2025 | 5 | Not Started | Activity patterns + bot detection
Model Evaluation Framework | Self | 08/04/2025 | 08/08/2025 | 5 | Not Started | Accuracy metrics + benchmarking
PHASE 3: INTEGRATION & DASHBOARD
Pipeline + Analytics Integration | Self | 08/11/2025 | 08/15/2025 | 5 | Not Started | Live analytics on Bluesky data
Dashboard Development | Self | 08/11/2025 | 08/18/2025 | 6 | Not Started | Web interface + visualizations
System Monitoring Setup | Self | 08/18/2025 | 08/22/2025 | 5 | Not Started | Health checks + alerting
Final Testing & Documentation | Self | 08/18/2025 | 08/25/2025 | 6 | Not Started | 1-week reliability test
Demo Preparation | Self | 08/25/2025 | 08/25/2025 | 1 | Not Started | Portfolio presentation materials